## Risk Register
ID | Risk statement | Category | Probability | Impact | Score | Owner | Response | Trigger | Status | Review date
R-001 | If requirements continue to expand after design sign-off, then configuration rework will push go-live by 4–6 weeks. | Scope | High | High |  | Project Manager | (Avoid): freeze scope at sign-off; all changes via change control with impact assessment | Any new requirement raised post-sign-off | Open
R-002 | If legacy time-keeping data is not cleansed before migration, then UAT will surface pay-rule defects late, delaying go-live. | Data | High | High |  | Data Lead | (Mitigate): two cleansing sprints before first mock load; reconciliation sign-off gates each load | Mock load reconciliation variances >0 | Open
R-003 | If the client payroll lead has no protected capacity, then design decisions will queue and the schedule will slip. | Resources | High | High |  | Executive Sponsor | (Mitigate): 50% capacity formally allocated in writing; backfill identified | Decision turnaround exceeds 5 business days | Open
R-004 | If the benefits carrier EDI file fails in integration testing, then enrollment data will require manual entry at go-live. | Technology | Medium | High |  | Integration Lead | (Mitigate): early carrier connectivity test in month 1; manual-entry contingency staffed | First connectivity test fails | Open
R-005 | If managers don't complete approval training, then time-off requests will bottleneck after go-live. | Change | Medium | Medium |  | Change Lead | (Mitigate): training completion tracked as go-live gate; manager champions per department | Training completion <90% at T-2 weeks | Open
R-006 | If Quebec-specific tax rules are misconfigured, then the first payroll will produce incorrect deductions. | Compliance | Medium | High |  | Payroll Lead | (Avoid): jurisdiction review workshop before design sign-off; parallel run includes Quebec scenarios | Parallel run variance in Quebec deductions | Open
R-007 | If the steering committee cannot reach decisions within one meeting cycle, then dependent workstreams will idle. | Governance | Medium | Medium |  | Project Manager | (Mitigate): decision log with due dates; escalation path to sponsor defined | Any decision open >10 business days | Open
R-008 | If the legacy system remains editable during the data freeze, then migration reconciliation will be invalidated. | Cutover | Medium | High |  | Cutover Manager | (Avoid): freeze communicated 4 weeks ahead; read-only access enforced technically | Any write detected during freeze window | Open

## Scoring Guide
Probability × Impact Scoring Matrix
Probability \ Impact | Low | Medium | High
High | 3 | 6 | 9
Medium | 2 | 4 | 6
Low | 1 | 2 | 3
Score = MATCH(probability, {"Low","Medium","High"}) × MATCH(impact, {"Low","Medium","High"}) → 1–9
Review Bands
7–9 · Red | Active mitigation plan, executive visibility, weekly review.
4–6 · Amber | Plan drafted, review biweekly.
1–3 · Green | Watchlist, review monthly.
Honest scoring: "When the context changes the probability, rescore — don't defend the old number (see R-006)."

## Review Cadence
Review Cadence
Weekly
Review red and amber risks in the project team meeting.
Steering Committee
Top risks are the first agenda item, every meeting.
Monthly
Full register review, including green watchlist items.
The Rule
A risk stays open until its mitigation is verified — the parallel run reconciled, the training completed, the freeze held. "Plan in progress" is not "mitigated."